14 High-Priority Gambling Markets for 2026

Direct B2C Licensing Only – No M&A/Consolidation Models

Your existing operations in Bulgaria, Mexico, and pending Peru license position you to execute a phased global expansion across Europe, Americas, Africa, and Southeast Asia. By executing simultaneous Q1 2026 applications across 7 markets, followed by strategic Q2-Q4 expansions, you'll establish a diversified portfolio generating USD 35M-60M+ in 2027.

Key Strategic Changes:

- M&A Removed: Brazil (USD 3.0B-3.5B) and Colombia (USD 650M-800M) removed from 2026 plan

- Direct B2C Focus: 14 markets via direct licensing, no partnerships or acquisitions

- European Expansion: Greece, Portugal, Denmark, Estonia

- Laos POGO Added: Unique offshore foreign-player targeting (USD 300K-800K+/month revenue potential)

- Capital Efficiency: USD 5.925M total 2026 investment

- Revenue Clarity: Direct B2C licensing provides predictable approval timelines and unit economics

Market Overview Matrix

Strategic Market Entry Matrix: 14 Direct B2C Licensing Markets – No M&A, Including EU Expansion & Laos POGO

The 14 Priority Markets

Tier 1: Urgent Q1 2026 Entry (7 Markets) – Foundation & First-Mover Windows

Strategic Focus: Execute 7 simultaneous applications capturing regulatory windows that close mid-2026 (Paraguay de-monopolization, Dominican Republic licensing closure) and establishing EU foundation (Malta, Ireland).

1. Malta – EUR 800M-1.0B | Q1 2026 | EU Passporting Gateway

- License Type: B2C Type 1-2 Remote Gaming

- Tax Rate: 5% (lowest EU)

- Approval Timeline: 8-12 weeks

- Capital Required: EUR 100K

- Annual Fee: EUR 25K/license

- Strategic Value: EU passporting = legal operations across 27+ EU countries from single license

- Revenue Target: USD 200K-400K/month (April 2026 onwards)

- Key Advantage: Foundation license enabling EU expansion to Spain, Italy, UK, etc.

2. Ireland – EUR 600M-800M | Q1 2026 | Zero Tax Entry

- License Type: B2C Casino/Sports Betting

- Tax Rate: 0% gaming tax (unique in EU)

- Approval Timeline: 30-60 days (fastest EU)

- Capital Required: EUR 40K

- Strategic Value: Fastest EU entry; zero-tax structure

- Revenue Target: USD 150K-250K/month (March 2026 onwards)

- Key Advantage: Approval arrives before Malta;

3. Panama – USD 400M-600M | Q1 2026 | Americas Gateway

- License Type: B2C Online Casino/Sports Betting

- Tax Rate: Competitive (market standard)

- Approval Timeline: 4-8 weeks

- Capital Required: USD 100K-200K

- Strategic Value: Central Americas positioning; established regulatory clarity

- Revenue Target: USD 150K-300K/month (April 2026 onwards)

- Key Advantage: Clear regulatory pathway; direct B2C licensing

4. Costa Rica – USD 300M-500M | Q1 2026 | Central America Expansion

- License Type: B2C Online Casino/Sports Betting

- Tax Rate: Moderate

- Approval Timeline: 4-8 weeks (parallel with Panama)

- Capital Required: USD 80K-150K

- Strategic Value: Geographic diversification; 10+ year regulatory stability

- Revenue Target: USD 100K-200K/month (May 2026 onwards)

- Key Advantage: Political stability; mature regulatory framework

5. Paraguay – USD 200M-350M | Q1 2026 | ⚠️ HIGHEST URGENCY

- Law: Law 7348/2025 (de-monopolization effective 2025)

- Regulator: Conajzar (new National Gaming Commission, actively welcoming operators)

- Tax Rate: LOWEST in Latin America

- Approval Timeline: 6-12 weeks

- Capital Required: USD 150K-300K

- Strategic Value: First-mover advantage in newly opened market; monopoly ended mid-2025

- Revenue Target: USD 200K-400K/month (May 2026 onwards)

- CRITICAL TIMING: De-monopolization window closes by mid-2026. Applications submitted Q1 have highest approval probability. Delay to Q2 risks missing early-mover window.

- Action Required: THIS WEEK – Engage Paraguayan counsel immediately; request licensing details from Conajzar

6. Dominican Republic – USD 600M-900M | Q1 2026 | ⚠️ Closing Window

- License Type: B2C Online Casino/Sports Betting

- Tax Rate: High (tourism-oriented)

- Approval Timeline: 8-12 weeks

- Capital Required: USD 150K-250K

- Market Size: USD 600M-900M (largest Q1 market)

- Strategic Value: Tourism-driven growth; tourism player base stability

- Revenue Target: USD 250K-400K/month (May 2026 onwards)

- CRITICAL TIMING: Government consolidating license base; licensing closes Q4 2026. Final entry window is Q1-Q2 2026.

- Action Required: Submit application by February 28, 2026 (before window closes mid-year)

7. Greece – USD 400M-600M | Q1 2026 | Mediterranean EU Entry (CONDITIONAL)

- License Type: B2C Type 1 Online Betting OR Type 2 Casino

- Tax Rate: ⚠️ 35% operator GGR (HIGHEST in EU) + progressive player winnings tax

- Approval Timeline: 8-12 weeks

- Capital Required: EUR 200K (minimum) + EUR 500K bank guarantee

- License Fees: EUR 3M (Type 1) or EUR 2M (Type 2) initial + renewal fees

- Strategic Value: Mediterranean player base; EU regulatory recognition

- Revenue Target: USD 100K-200K/month (cautiously conservative due to high tax)

- ⚠️ MAJOR CAVEAT: 35% operator tax is unsustainable for new entrants

  - Comparable to Romania (which we removed due to broken economics)

  - 69-82% of Greek bets still on unlicensed operators (high player tax drives offshore activity)

  - Unit economics severely compressed at 35% tax rate

- CONDITIONAL RECOMMENDATION: Only pursue if financial modeling demonstrates profitability at 35% tax rate. If not viable, replace with Denmark/Estonia/Portugal in Q2 instead.

- Alternative: If Greece rejected = allocate resources to stronger Q2 EU markets (Denmark, Estonia, Portugal)

Tier 2: Q2 2026 Secondary Markets (4 Markets) – EU Expansion & Africa Entry

Strategic Focus: Leverage Q1 momentum with secondary EU markets plus Africa entry point (Kenya).

8. Portugal – USD 300M-400M | Q2 2026 | Mediterranean EU (8% Tax)

- License Type: B2C Online Casino/Sports Betting

- Regulator: SRIJ (Gaming Regulation and Supervision Service)

- Tax Rate: 8% IEJO (Electronic Gaming Tax) – 2nd best in EU after Ireland's 0%

- Approval Timeline: 6-12 months (longest of any Q2 market)

- Capital Required: EUR 50K-100K (estimate)

- Annual Supervisory Fee: EUR 20K-40K (estimate)

- License Duration: Long-term (not annual renewal)

- Strategic Value: Mediterranean positioning (complements Malta northern EU focus); sustainable 8% tax rate

- Revenue Target: USD 80K-200K/month (October 2026 onwards – delayed timeline due to 6-12 month approval)

- Timeline: Submit April 2026 = approval October 2026-February 2027

- Advantage: If Greece's 35% tax proves unviable, Portugal becomes superior Mediterranean alternative with manageable 8% tax

- Key Note: Online licenses available without numerical restriction; processing timeline is main barrier

9. Denmark – USD 500M-700M | Q2 2026 | Scandinavian Premium Market

- License Type: B2C Betting license, Online casino license, or Combined

- Regulator: Danish Gambling Authority (Spillemyndigheden)

- Tax Rate: 20% GGR (moderate for EU)

- Approval Timeline: 60-90 days

- Capital Required: DKK 1-2M (~EUR 130K-270K) estimate

- Application Fees: DKK 304,500 (~EUR 41K) per license type; DKK 426,300 (~EUR 57K) combined

- Gaming System: Must be located in Denmark (infrastructure requirement)

- Data Repository: SAFE system required (real-time regulatory data access)

- Strategic Value: Premium Scandinavian player base; clear regulatory pathway; mature market

- Revenue Target: USD 150K-300K/month (September 2026 onwards)

- Infrastructure Note: Budget EUR 50-100K for gaming server infrastructure in Denmark (Copenhagen/Aarhus area)

- Advantage: Strong market fundamentals; clear regulatory process

10. Estonia – USD 200M-300M | Q2 2026 | Digital-Forward EU Market

- License Type: B2C Online Casino/Sports Betting

- Tax Rate: 20% GGR

- Approval Timeline: 8-12 weeks (faster than Denmark)

- Capital Required: EUR 50K-100K (estimate)

- Strategic Value: Digital-forward regulatory environment; tech-friendly jurisdiction (highest e-government maturity in EU)

- Revenue Target: USD 60K-150K/month (August 2026 onwards)

- Market Size: Smaller than Denmark/Portugal (USD 200M-300M) but serves as Baltic region entry point

- Advantage: Fast approval; lower capital requirement; gateway to Latvia/Lithuania expansion

11. Kenya – USD 153M | Q2 2026 | Africa Entry Point (6.9% CAGR – Fastest Africa Growth)

- License Type: B2C Sports Betting (primary), Casino (secondary)

- Regulator: BCLB (Betting Control and Licensing Board)

- Tax Rate: 20% standard

- Approval Timeline: 8-12 weeks

- Capital Required: USD 500K-2M (lowest Africa market entry cost)

- Local Ownership: 30% required (partner with Kenyan entity)

- Unique Advantage: M-Pesa integration (world's most sophisticated mobile money system) enables seamless payment processing

- Market Characteristic: Mobile-first (sports betting = 70% of market demand)

- Strategic Value: Africa entry point; fastest-growing African market; proven regulatory clarity

- Revenue Target: USD 100K-300K/month (June 2026 onwards)

- Why Kenya First (Not South Africa)?

  - Faster growth rate (6.9% CAGR vs. South Africa 4.6%)

  - Simpler regulatory pathway (BCLB less demanding than South Africa's NGB)

  - Lower capital requirement (USD 500K-2M vs. South Africa USD 2M-5M+)

  - Operational learning before Nigeria/South Africa expansion

  - M-Pesa ecosystem provides distinctive payment advantage

- Key Insight: Sequential Africa strategy (Kenya → Nigeria Q3 → South Africa Q4 application) optimizes learning and capital deployment

Tier 3: Q3-Q4 2026 Growth & Positioning Markets (3 Markets) – Africa Expansion & Southeast Asia

Strategic Focus: Africa scaling (Nigeria), Southeast Asia offshore positioning (Laos POGO), plus South Africa application for 2027 launch.

12. Nigeria – USD 176M | Q3 2026 | Fastest African Growth (7.4% CAGR)

- License Type: B2C Multi-State (Lagos + Ogun + FCT)

- Regulators:

  - Lagos State Lotteries Board (sports betting)

  - NLRC (National Lottery Regulatory Commission, federal – online casino)

- Tax Rate: Variable by state (estimated 15-20%)

- Approval Timeline: 4-8 weeks per license

- Capital Required: USD 500K-1M total

- Licensing Costs:

  - Sports Betting (Lagos): NGN 100M (~USD 67K) + NGN 2M application

  - Federal Casino (NLRC): NGN 100M (~USD 67K) + NGN 2M application

  - Association member discount: 50% reduction available (USD 33.5K per license)

- Multi-State Expansion: Phase 2 (Q4 2026) adds Ogun State + FCT with minimal incremental cost

- Market Characteristic: Sports-betting focused (80% of market), young demographic (median age 18.5), fastest African growth

- Strategic Value: Largest African growth opportunity; federated licensing model recently clarified (2025 – removed previous confusion)

- Revenue Target: USD 150K-400K/month (July 2026 onwards, scaling with multi-state expansion)

- Key Insight: Why Q3 (not Q2)? Kenya learning in Q2 informs Nigeria strategy; sequential Africa expansion optimizes execution

- Competitive Position: 70+ existing licensed operators demonstrate market viability and proven regulatory path

13. Laos – USD 150M+ | Q3-Q4 2026 | POGO Offshore Foreign-Player Model

UNIQUE STRATEGIC ASSET: Laos is NOT a traditional B2C market but a POGO (Philippine Offshore Gaming Operator) -style offshore licensing uniquely positioned for foreign-player targeting across Southeast Asia.

Why Laos is Strategically Different:

Regulatory Model:

- Online Gambling: ✅ EXPLICITLY LEGAL for foreign operators serving foreign players ONLY

- Domestic Gambling: ❌ Prohibited for Laotian citizens

- Target Markets: Thailand (70M pop, online prohibited), Vietnam (100M pop, online prohibited), Myanmar, Cambodia

- Addressable Players: Estimated 50-100M+ Southeast Asian players currently using offshore sites

Licensing Framework:

- Authority: Ministry of Planning and Investment (MPI) + Laos Offshore Gaming Authority (LOGA, established 2022)

- License Duration: 10-20 years (negotiated)

- Operating Model: Foreign operators serving foreign players only (POGO structure)

- Tax Structure: ~10-15% estimated (lower than Philippines PAGCOR which operators are abandoning)

- Application Process: Moderate complexity (more than direct B2C, less than M&A)

Market Opportunity:

- Geographic Reach: Thailand, Vietnam, Myanmar, Cambodia

- Competitive Positioning: Laos government actively encouraging migration from Philippines POGOs (which face higher taxes + China pressure)

- Revenue Potential: USD 300K-800K+/month (exceeds single small-market B2C licensing due to multi-country player base)

- Current Status: LOGA licensed 2022; accepting new operator applications; government supports liberalization

Entry Strategy:

Phase 1: POGO Licensing (Q3-Q4 2026)

- Engage Lao gaming counsel; contact LOGA for licensing pathway

- Prepare comprehensive POGO application (business plan, financial projections, responsible gambling framework, market targeting)

- Submit to MPI and Gaming Commission

- Negotiate tax structure and license terms (10-20 year duration)

- License award expected December 2026

Phase 2: Platform & Regional Operations (Q4 2026-Q1 2027)

- Develop offshore platform supporting multi-country compliance (Thailand/Vietnamese localization)

- Regional player acquisition (Thai/Vietnamese language marketing, local payment methods)

- Payment infrastructure: Thai banking, Vietnamese banking, regional e-wallets, cryptocurrency

- Responsible gambling compliance (AML, KYC, player protection aligned to offshore POGO standards)

Product Offering:

- Sports betting (primary, 70%+ of POGO revenue): Thai football, Vietnamese football, Asian leagues, international sports

- Casino games (secondary, 20-30%)

- Esports betting (growing in Southeast Asia)

Timeline:

- Q3 2026: POGO licensing application preparation

- Q4 2026: License award and platform development

- Q1 2027: Operational launch serving Thailand/Vietnam/Myanmar/Cambodia

Target Approval Date: December 31, 2026

Post-Launch Revenue (2027 onwards): USD 300K-800K+/month estimated (significantly exceeds single-market B2C due to multi-country addressable player base)

Strategic Rationale for Laos:

- Not a gray market: Explicitly legal offshore licensing (unlike unregulated offshore)

- Multi-country leverage: Single license serves 50-100M+ player base across 4+ countries

- Revenue upside: Exceeds individual Malta/Ireland/Panama licensing revenue (which generate USD 150K-400K/mo single-market)

- Regional hub positioning: Positions you as Southeast Asia operator alongside individual country presence (Kenya/Nigeria/South Africa Africa hub)

- Capital efficiency: Laos POGO infrastructure investment (USD 300K-600K) generates revenue equivalent to 2-3 individual B2C markets

Why Q3-Q4 (Not Q1):

- POGO licensing is more complex than direct B2C (negotiated tax structure, multi-country compliance)

- Platform development for multi-country operations requires extended prep time

- Kenya success (Q2) provides learning before Laos regional expansion

- Tax structure negotiation happens during Q3-Q4 application window

14. South Africa – USD 296M | Q4 2026 Application | Q2-Q3 2027 Launch

Strategic Positioning: South Africa is Africa's most developed and mature gambling market. Q4 2026 licensing application targets Q1 2027 approval and Q2-Q3 2027 operational launch.

Market Characteristics:[6][7][8]

- Regional Hub: Operates as Southern Africa operational center (Botswana, Namibia, Zimbabwe access)

- Regulatory Maturity: 60+ licensed casinos; sophisticated compliance framework

- Esports Leadership: Only African market with significant esports betting infrastructure

- Market Size: USD 296M (moderate for Africa)

- Growth Rate: 4.6% CAGR (slowest of three Africa entries, but most developed)

License Specifications:

- Type: B2C Online Casino/Sports Betting

- Regulator: National Gambling Board (NGB)

- Tax Rate: 10-20% (variable by province)

- Capital Requirement: USD 2M-5M+ (highest of Africa markets)

- Approval Timeline: 12-16 weeks (longest approval timeline)

Entry Strategy:

- Q4 2026: Submit B2C license application to NGB

- Q1 2027: Expected approval (12-16 weeks post-submission)

- Q2-Q3 2027: Operational setup and platform launch

Why South Africa is Tertiary (Q4 Application, Not Q2 Direct Licensing):

- Lower growth rate (4.6% vs. Kenya 6.9%, Nigeria 7.4%)

- Higher capital requirement (USD 2M-5M+ vs. Kenya USD 500K-2M)

- More rigorous compliance requirements (NGB enforcement more demanding than BCLB/NLRC)

- Sequential Africa strategy (Kenya → Nigeria → South Africa) optimizes learning and capital deployment

- Q1 2027 approval allows capital generation from Kenya/Nigeria operations to fund South Africa launch

- South Africa serves as premium Africa consolidation hub after Kenya/Nigeria success

Post-Launch Revenue (Q2-Q3 2027 onwards): USD 250K-600K/month estimated

Market Entry Timeline & Revenue Projection

Q1 2026 (January-March): Foundation Launch

Markets Launching: Malta, Ireland, Panama, Costa Rica, Paraguay, Dominican Republic, Greece (if viable)

- Simultaneous Applications: 7 markets

- Expected Approvals: Ireland (late Feb), Malta/Panama/Costa Rica (late Mar), Paraguay/Dominican Republic (Apr)

- Operating Revenue: Bulgaria + Mexico existing (USD 500K-800K/month)

- New Approvals: First revenues arriving late Q1

- Revenue Run-Rate by March 31: USD 500K-800K/month

Q2 2026 (April-June): Q1 Expansion + Secondary Wave

Markets Launching: Portugal (application), Denmark, Estonia, Kenya
Q1 Approvals Operational: Malta, Ireland, Panama, Costa Rica, Paraguay, Dominican Republic (6 markets now live)

- Operating Markets: Bulgaria + Mexico + 6 Q1 launches = 8 total

- New Approvals: Denmark (Aug approval but application Q2), Estonia (Jul approval but application Q2), Kenya (May approval)

- Operating Revenue: Q1 launches ramping (Malta/Ireland/Panama/Costa Rica ramping May-June)

- Revenue Run-Rate by June 30: USD 1.0M-2.0M/month

Q3 2026 (July-September): Africa & Asia Expansion

Markets Launching: Nigeria (multi-state), Laos POGO (application)
Q2 Approvals Operational: Denmark (Aug), Estonia (Jul), Kenya (May, now ramping)

- Operating Markets: 8 existing + 3 Q2/Q3 approvals = 11+ markets

- Revenue Contributors: Kenya (ramping Jun-Sep), Denmark (ramping Sep-Oct), Estonia (ramping Aug-Sep)

- New Approvals: Nigeria (Jun approval), Laos POGO (application stage, Oct-Nov)

- Operating Revenue: 11+ markets operating; Q2 launches ramping

- Revenue Run-Rate by September 30: USD 1.5M-3.0M/month

Q4 2026 (October-December): Consolidation & Positioning

Markets Launched: Nigeria operations expanding to multi-state; Laos POGO application finalizing
South Africa: License application submitted (approval expected Q1 2027)

- Operating Markets: 13 operational (including Laos if early launch); 1 application (South Africa)

- Portugal Status: Approval likely October 2026 or delayed to Q1 2027

- Laos POGO Status: License award expected December 2026

- Operating Revenue: 13+ markets operating; Nigeria expanding to multi-state

- Revenue Run-Rate by December 31: USD 3.5M-4.5M/month

- Full Year 2026 Revenue: USD 16.5M-31M estimated

Capital Investment & Budget Summary

| Category | Q1 | Q2 | Q3 | Q4 | 2026 Total |
| --- | --- | --- | --- | --- | --- |
| Licensing/Application Fees | $175K | $200K | $150K | $50K | $575K |
| Legal & Compliance | $350K | $250K | $200K | $150K | $950K |
| Operational Setup | $300K | $350K | $300K | $250K | $1.2M |
| Technology & Platform | $150K | $150K | $150K | $200K | $650K |
| Laos POGO Infrastructure | — | — | $300K | $300K | $600K |
| Marketing/Launch | $100K | $300K | $400K | $400K | $1.2M |
| Contingency (15%) | $200K | $200K | $200K | $150K | $750K |
| TOTAL QUARTERLY | $1.275M | $1.45M | $1.7M | $1.5M | $5.925M |

Total 2026 Direct B2C Market Entry Investment: USD 5.925M

Expected Revenue Progression

2027 Projected Annual Revenue: USD 35M-60M+ (including South Africa launch Q2-Q3 2027)

Key Consolidation Model

| Factor | Direct B2C Only (This Plan) |
| --- | --- |
| Total 2026 Investment | USD 5.925M |
| Markets Licensed | 14 direct licenses |
| Brazil/Colombia | Excluded (M&A-only entry) |
| Approval Timeline Predictability | HIGH (regulatory timelines clear) |
| Execution Risk | LOW (follow licensing pathway) |
| Revenue Timing Clarity | Q1-Q4 2026 phased (predictable) |
| Unit Economics | Clear per-market (direct licensing) |
| Operational Complexity | 14 separate P&Ls |

Direct B2C for 2026 – Lower capex, faster execution, clearer timelines, better suited to 2026 deployment given regulatory windows (Paraguay, Dominican Republic) closing mid-year.

Critical Success Factors

1. Q1 2026 Simultaneous Execution (URGENT)

Action Required This Week (January 12-19, 2026):

- Engage legal counsel in Malta, Ireland, Panama, Costa Rica, Paraguay, Dominican Republic, Greece (if viable)

- Prioritize Paraguay (de-monopolization window closing) and Dominican Republic (licensing closes Q4)

- Submit all 7 applications by end of January to capture Q1-Q2 approval windows

Timeline Impact:

- Each week of delay = 1-week loss in approval timing

- Parish regulatory windows (Paraguay de-monopolization, Dominican Republic licensing) close mid-2026

- Late submission risks missing first-mover advantages and regulatory closure

2. Greece Conditional Decision (This Week)

Financial Modeling Required:

- 35% operator GGR tax is unsustainable unless market commands premium pricing

- Compare unit economics vs. alternative Q2 markets (Denmark, Estonia, Portugal)

- Decision: Greece Q1 OR allocate Q1 resources to stronger Q2 alternatives

- Recommendation: Unless financial modeling demonstrates profitability at 35% tax, replace Greece with Denmark/Estonia in Q2

3. Regional Hub Strategy

- Europe: Malta (EU foundation) + Ireland (zero tax) + secondary markets (Denmark, Estonia, Portugal)

- Americas: Panama + Costa Rica (Central America) + Paraguay (South America) + Dominican Republic (Caribbean)

- Africa: Kenya (entry) → Nigeria (expansion) → South Africa (premium hub)

- Southeast Asia: Laos POGO (regional offshore targeting Thailand/Vietnam/Myanmar/Cambodia)

4. Sequential Market Strategy Discipline

- Q1 Approvals → Q2 Operations (May-June revenue ramping)

- Q2 Approvals → Q3 Operations (July-September revenue ramping)

- Q3 Approvals → Q4 Operations (October-December revenue ramping)

- Allows capital from Q1-Q2 approvals to fund Q3-Q4 launches

5. Regulatory Relationship Management

- Single point of contact per market (not rotating personnel)

- Monthly compliance reporting

- Early engagement with regulators on operational plans

Recommended Action Plan: Next 30 Days

Week 1-2 (January 12-25, 2026): Legal Engagement

- Parallel Action: Engage legal counsel in all 7 Q1 markets

- Priority Order: Paraguay (most urgent), Dominican Republic (closing window), Malta (EU foundation), Ireland, Panama, Costa Rica, Greece (conditional)

- Deliverable: Formal engagement letters signed; initial compliance documentation requests submitted

Week 2-3 (January 19-31, 2026): Application Preparation

- Paraguay: Request detailed licensing requirements from Conajzar; prepare urgent application

- Dominican Republic: Prepare comprehensive licensing application

- Malta/Ireland: Prepare System Documentation Checklists and application packages

- Panama/Costa Rica: Prepare standard licensing applications

Week 3-4 (January 26-February 2, 2026): Submission Phase

- Submit Applications: All 7 Q1 markets

- Track Status: Monthly regulator check-ins; approval timeline monitoring

- Prepare Q2 Pipeline: Begin prep for Denmark, Estonia, Kenya applications (Q2 submission April-May)