2026 Expansion Plan: Summary

Pros

- Time-Sensitive Market Capture: Prioritizes markets with closing windows, such as Paraguay (6–12 month de-monopolization) 1111and the Dominican Republic (licensing closes Q4 2026)2222.

- Regulatory Efficiency: Targets high-speed or low-tax jurisdictions like Ireland (30–60 day approval) 3and Paraguay (lowest tax in Latin America)4.

- Operational Synergies: Uses existing experience in Mexico and Bulgaria to bolster credibility for M&A in Brazil and partnerships in Colombia5555555555555555.

- Staggered African Growth: Uses Kenya as a hub to train teams before entering the high-growth Nigerian and South African markets6666.

Cons & Risks

- High Capital Requirements: The 2026 budget ranges from USD 13.8M to 47.2M 7777, with Brazil alone requiring up to USD 65M for acquisition and setup8.

- Resource Front-Loading: Attempting five simultaneous Q1 applications (Ireland, Panama, Costa Rica, Paraguay, Dominican Republic) will heavily tax your legal and compliance teams9.

- M&A Reliance: Success in the largest markets (Brazil, Colombia) is dependent on successful negotiations and due diligence rather than direct licensing101010101010101010.

Q1–Q2 2026 Latin American Application Timeline

This timeline focuses on direct B2C licensing in Q1 and transitions to M&A/Partnerships in Q2.

Q1 2026: The Licensing Sprint

- January (Weeks 1–3):

- Engage Counsel: Appoint specialized gaming legal teams in Panama, Costa Rica, Paraguay, and the Dominican Republic11111111111111111111111111111111.

- Requirement Requests: Request specific tender timelines and updated financial requirements from Conajzar (Paraguay)12121212.

- January (Week 4) – February (Week 2):

- Document Preparation: Compile financial statements, technical specs, and compliance policies for all four markets13131313131313131313.

- Submit Paraguay Application: High urgency to submit by early February to capture the first-mover window14141414.

- February (Weeks 3–4):

- Submission Phase: Submit formal applications to gaming authorities in Panama, Costa Rica, and the Dominican Republic151515151515151515.

- March:

- Panama Approval Target: Expected license award for Panama16.

- Paraguay Approval Target: Initial approvals expected from Conajzar17.

Q2 2026: Launch & Strategic Entry

- April:

- Dominican Republic Approval Target: Deadline to secure license before the window begins to tighten18.

- Panama Launch: Operational kickoff for Central American hub19.

- May:

- Costa Rica Approval Target: Expected licensing and transition to operational setup20202020.

- Paraguay Launch: Commercial launch to capture market share before saturation21.

- June:

- Brazil M&A: Begin due diligence on 4–6 identified mid-sized target operators (5–10% market share)22222222.

- Colombia Partnership: Evaluate minority stake (15–30%) in existing licensed Colombian operators23232323.

Specific Documentation Requirements

Panama (Direct B2C License)

- Financial Records: Audited financial statements demonstrating solvency24.

- Compliance Policies: Comprehensive AML/KYC and responsible gambling frameworks25.

- Technical Infrastructure: Detailed documentation of the gaming platform and security measures26.

- Mexico/Bulgaria Proof: Evidence of current successful operations to establish operator credibility27.

Paraguay (High Urgency De-Monopolization)

- Financial Viability: Proof of sufficient financial backing to meet Conajzar’s new standards282828.

- Clean Legal Record: Documentation proving no outstanding domestic or international legal debts29.

- Industry Experience: A dossier detailing your history and success in the gambling industry (utilizing Mexico/Bulgaria data)30.

- Certified Systems: Proof that electronic gaming systems comply with Conajzar-certified technical standards31.

- Physical Infrastructure: Certification that any local physical operations are at least 200m away from educational facilities32.

- Responsible Gambling: Specialized technical architecture for player protection and monitoring33.